## Master
2025 Revised Strategic workplan for the CCAML Scientific Committee, organised by science required to implement Article II of the CAMLR with topics allocated to Working Groups. "x" indicates the topic is addressed by the working group and names indicate the leadership role in progressing the work. | Urgency | ASAM | ASAM Progress | SAM | EMM | EMM Progress | IMAF | FSA | Workshop | Secretariat support
1. Target species
a) Develop methods to estimate biomass for krill | High | [8 empty] | Y
i) Survey design standards for regional and synoptic surveys |  | x | In progress
ii) Develop methods to use fishing fleets as monitoring platforms |  | x | In progress
ASAM Task 1: Methods for calibrating echosounders on fishing vessels | High | Dr Macaulay, Dr Fielding | In progress
ASAM Task 2: Survey design for fishing fleets | High | Linked to 1.a.i | In progress
ASAM Task 3: Develop the use of krill length frequency data in the estimation of target strength and krill weight for biomass estimates including seasonal and regional effects of developmental stage | High | x | In progress
ASAM Task 4: Develop protocols and timeline for delivering krill biomass estimates from surveys for inclusion in Krill Fishery Management Approach (KFMA) |  | x | [7 empty] | Y
ASAM Task 5: Develop spatial estimators for acoustic biomass data |  | x
iii) Data collection – SISO, vessels, and CEMP, including climate change parameters. (WS-CC-23 Table 1 Recommendation 5) | High |  |  | x | Dr Zhu, Dr Kawaguchi, Dr Collins, Dr Meyer | In progress |  |  |  | Y
SAM Task 1: Effective sampling to estimate length-frequency distribution | High |  |  | Ms Robson, Dr Kawaguchi
(1) Implement standardised surveys |  | x
(2) Develop diagnostic approaches for data quality | High | x |  |  | x
iv) Acoustic data storage and processing | High | Dr Cox, Dr Wang | [7 empty] | Y
(1) Identify metadata | High | x | In progress | [6 empty] | Y
(2) Acoustic raw data storage requirements and processing |  | x | In progress | [6 empty] | Y
(3) Automated data processing of acoustic data from fishing vessels, including frequency of updates to biomass estimates | Low | Dr Menze, Dr Wang, Dr Fielding | [7 empty] | Y
(4) Standardised procedures to check and verify acoustic data | Medium | Dr Macaulay
(5) Develop the use of krill length frequency data in the estimation of target strength, and krill weight for biomass estimates | High | x |  |  | x
(6) Submission of acoustic data and the inclusion of metadata by Members in the repository held by the Secretariat |  | Annex 4, Table 2, 1.a.iv.1 | [7 empty] | Y
(7) Develop statistical approaches to acoustic data emerging from new acoustic observation platforms | Low | Dr Menze, Dr Dornan | In progress
v) Biomass estimation methods | High | Dr Ying | In progress
(1) Establish Grym parameters for krill stock assessments in Areas 48 and 58 | High |  |  |  | Mr Maschette | In progress
(2) Krill age interlaboratory comparisons |  |  |  |  | x
(3) Grym Training
(4) Krill biomass estimate in Division 58.4.1 | Low | Dr Cox, Dr Murase
(5) Krill biomass estimate in Division 58.4.2 | Low | x
vi) Account for spatial structure of krill | Medium |  |  |  | Dr Schaafsma, Dr Panasiuk, Dr Zhu | In progress
b) Develop stock assessments to implement decision rules for krill |  |  |  | x |  |  |  | x
SAM Task 2: Development of integrated stock assessment for krill | Medium |  |  | Mr Mardones
i) Krill management approach (synthesis of krill recruitment, spatial scale, biomass estimates, predator risk) | High | x |  |  | Dr Kawaguchi, Dr Meyer | In progress
(1) Subarea 48.1 (2022) | High | x
(2) Subareas 48.2, etc… (2023/24) | Medium | x
ii) Develop diagnostic tools | Medium | x |  |  | Mr Maschette | Not yet started
iii) Develop ecosystem indicators to inform risk assessment framework |  |  |  |  | Dr Warwick-Evans
iv) Methods to account for uncertainty in stock status | Low | x |  |  | x | Not yet started
(1) Advection of krill (flux) | Medium | Dr Kasatkina
(2) Spatial structure within subareas |  | Dr Ying
(3) Interannual variability |  | x
(4) Vertical distribution |  | x
(5) Seasonal variability |  | x
(6) Sampling design power to detect changes in krill distribution
v) Develop krill fishery management approach as a multiannual cycle |  | ? |  |  | x
vi) Generate precautionary spatial catch limits for krill |  |  |  |  | x
vii) Krill management strategies that are robust to climate change | Medium |  |  |  | Dr Hill | In progress
viii) Develop a framework for using climate models to drive ecological projections for AMLR and dependent and related species (WS-CC-23 Table 1 Recommendation 12) | High |  |  |  | SCAR | In progress
c) Develop methods to estimate biomass for finfish |  | x |  | x
i) Survey design for finfish | Medium | Dr Kasatkina |  | x
SAM Task 3: Evaluate tagging performance using different gear types | Medium |  |  | Dr Péron, Dr Masere, Dr Kasatkina | [5 empty] | Y
ii) Data collection – SISO & vessels | High | x |  | x |  |  |  | x
SAM Task 4: Metrics of vessel tagging performance | Medium |  |  | Dr Péron, Dr Masere, Mr Dunn | [5 empty] | Y
(1) Conversion factors | Mostly done |  |  | x |  |  |  | Secretariat, France, New Zealand |  | Y
SAM Task 6: Develop protocol for conversion factors | High |  |  | Mr Gasco, Dr Massiot-Granier, Mr Walker |  |  |  | x |  | Y
(2) Tagging protocols | Completed | [6 empty] | Dr Jones, Mr Arangio |  | Y
(3) Ross Sea data collection program | Medium | [6 empty] | New Zealand |  | Y
iii) Improve biomass estimation methods for finfish |  | Dr Wang |  | x
SAM Task 7: Evaluate bias in tagging data in abundance estimation | Medium |  |  | Dr Masere, Dr Péron, Dr Devine
SAM Task 8: Vessel configuration factors affecting tagging mortality | Medium |  |  | Dr Masere, Dr Péron, Dr Devine | [5 empty] | Y
iv) Improved observations as inputs for stock assessment |  |  |  | x
SAM Task 9: Estimation of sample size requirements per age class for an ageing reference set | Medium |  |  | Dr Devine, Dr Quiroz, Mr Sarralde | [5 empty] | Y
v) Gear standardisation analyses for finfish |  |  |  | x
vi) Modelling of spatial population structure for finfish |  |  |  | x
(1) Accounting for potential spatial bias in assessments | Urgent |  |  | x |  |  |  | x
vii) Connectivity of target and non-target species using new technologies
(1) Pop-up satellite tag investigations | Low/Medium | [6 empty] | x
(2) Otolith microchemistry | Low/Medium | [6 empty] | x
(3) Microsatellite markers and population genomic analyses | Low/Medium | [6 empty] | x
(4) Emerging technologies | Low/Medium | [6 empty] | x
viii) Review regulatory framework
d) Develop stock assessments to implement decision rules for finfish |  |  |  | x
i) Research to develop new assessments | Low |  |  | x |  |  |  | x
(1) Research plan evaluations | High | x |  | x |  |  |  | x |  | Y
(2) Subarea 88.2 fishery structure | Low | [6 empty] | New Zealand
(3) Stock structure and connectivity | Low | [6 empty] | Japan, Australia, China, Korea, USA
ii) Develop new assessment tools |  |  |  | x
(1) CASAL2 development | Complete |  |  | x |  |  |  | New Zealand
(2) Toothfish age interlaboratory comparisons |  |  |  | x |  |  |  | x
(3) CASAL2 data limited assessment | High |  |  | x |  |  |  | South Africa, Spain, Japan
iii) Provide precautionary catch limits | High |  |  | x |  |  |  | x |  | Y
iv) Developing sex disaggregrated assessment modesl for areas with combined sex assessments | Medium |  |  | x
e) Management strategy evaluations for target species (Performance Review 2, Rec 8) |  |  |  | x |  |  |  | x
i) Evaluation of the CCAMLR decision rules for finfish and potential alternative harvest control rules for assessed fisheries using MSE (SAM Task 12) | High |  |  | Dr Ziegler, Mr Dunn, Dr Massiot-Granier, Dr Earl, Mr Somhlaba, Dr Masere, Ms Ouzoulias |  |  |  | x
(1) Workflow with Climate change effect on management (T17-8 from WS-CC-2023) | Medium | [6 empty] | x
(2) CCAMLR Decision Rules for finfish with temporal change of recruitment (T17-22 from WS-CC-2023) | Medium | [6 empty] | x
(3) Uncertainty relating Climate change in CCAMLR Decision Rules (T18-10 from WS-CC-2023) | Medium | [6 empty] | x
ii) Development and testing of data-limited fishery decision rules (SAM Task 13) | Medium |  |  | Dr Ziegler, Mr Dunn, Dr Massiot-Granier, Dr Earl, Mr Somhlaba, Dr Masere |  |  |  | x (WG-FSA-2024, paragraph 7.2) |  | Y
iii) Finfish management strategies that are robust to climate change | Medium (SAM/EMM), Urgent (FSA) |  |  | x | Dr Devine |  |  | Australia, NZ, UK |  | Y
iv) Analysis of current and alternative decisions rules | High |  |  | x | [5 empty] | Y
v) Management Strategy Evaluations for krill | Medium |  |  |  | Mr Mardones, Dr Lowther, Mr Johannessen
f) Krill Stock Hypothesis Information Collection Plan (see EMM-2023 Table 1) |  |  |  |  | x
g) Refine stock assessment procedures
i) Improve methods for inclusion of ageing data | Medium |  |  | x
(1) Determining the CVs on the age compositions and effective sample sizes | [7 empty] | x
(2) Determining the effect of different target levels of precision for age determination | [7 empty] | x
ii) Incorporating environmental and ecosystem parameters in toothfish population models | Medium | [6 empty] | x
iii) Investigate the impact of co-varying productivity parameters. | Medium | [6 empty] | x
iv) Continue development of stock assessment diagnostics | High | [6 empty] | x
v) Develop methods to validate and pool multimember age data | High | [6 empty] | x
(1) Determining how differences in toothfish growth over time impacts age interpretation | [7 empty] | x
h) Develop methods to estimate climate change effects on harvested species
i) to identify data-sharing needs with adjacent RFMOs to detect effects of climate change, e.g. species (WS-CC-23 Table 1 Recommendation 1, 2) | High | [6 empty] | x |  | Y
ii) Identify any non-target species within the CAMLR Convention Area likely to increase in commercial importance. (WS-CC-23 Table 1 Recommendation 4) | High | [6 empty] | x |  | Y
iii) To develop methods to incorporate the effects of projected climate change on assumed recruitment patterns or uncertainty for harvested species recruitment into assessment projections. (WS-CC-23 Table 1 Recommendation 6) | Medium | [6 empty] | x
2. Ecosystem impacts
a) Ecosystem monitoring (Performance Review 2, Rec 5) |  | x |  | x | x |  | x | x |  | Y
i) Structured ecosystem monitoring programs (CEMP, fishery) | High | x |  | x | Dr Collins, Dr Hinke, Dr Lowther, Dr Hill | In progress |  | x
SAM Task 14: Effective sample size estimation for monitoring fish by-catch in the krill fishery |  |  |  | Dr Jones | [5 empty] | Y
(1) Develop a data collection plan for KFMA and D1MPA | High | x |  |  | Dr Krüger, Dr Santos, Mr Santa Cruz, Dr Lowther, Dr Meyer, Dr Zhu, Dr Krause, Dr Kasatkina |  |  |  |  | Y
(2) CEMP Review Teams
i. Analysis of existing data | High |  |  |  | Dr Hill, Dr LaBrousse | In progress |  |  |  | Y
ii. Sentinel Species Monitoring team | High |  |  |  | Dr Emerson | In progress
iii. Krill fishery and at-sea data collection plan team | High |  |  |  | Dr Kawaguchi | In progress
iv. External Data of Relevance to CCAMLR team | High |  |  |  | Dr van de Putte | In progress |  |  |  | Y
v. Analysis of Tracking data team | High |  |  |  | Dr Krüger | In progress
vi. Cetacean Monitoring team | High |  |  |  | Dr Lowther Dr Kelly | In progress
(2) CEMP related products for use by other working groups |  | x
i. Area 48 | High |  |  |  | Dr Waluda, Dr Santos, Dr Krüger | In progress
ii. Other areas (58, 88) |  |  |  |  | Dr Van de Putte, Dr Labrouse
(3) Fishery via SISO related products for use by other working groups | Medium | x |  |  | Dr Van de Putte, Dr Emmerson, Dr J. Kim |  | x | x |  | Y
IMAF Task 7.1 Consider IMAF-related tasks for observers in the various CCAMLR fisheries | High | [5 empty] | x
IMAF Task 7.2 Consider use of EM and AI to improve the efficiency of data collection to aid observers | Low | [5 empty] | Mr Clark |  |  | Y
(4) Research surveys | Medium | x |  |  |  |  | Mr Clark | x
IMAF Task 9.1 Consider options for the management of light pollution for vessels fishing in the Convention Area | Low | [5 empty] | Ms Livesey
ii) Ecosystem modelling | Low |  |  |  | x | In progress
iii) Invasive species | Low |  |  |  | x |  |  | x
iv) Marine debris monitoring | Low |  |  |  | Dr Waluda, Dr Schaafsma, Dr Makhado, Dr Emmerson, Dr Santos, Mr Pardo | In progress |  |  |  | Y
IMAF Task 8.1 Review information on the effect of marine debris on marine mammals and seabirds in the Convention Area | High | [5 empty] | Ms Livesey |  |  | Y
v) Ecosystem effects of extreme events |  |  |  |  | x
(1) Develop a catalogue of the different types of extreme events, their time scales and the species and life stages that they are likely to affect and propose management responses (WS-CC-23 Table 1 Recommendation 13, 14) |  |  |  |  | x
(2) Collate a list of important variables to be monitored following an extreme event (WS-CC-23 Table 1 Recommendation 15) |  |  |  |  | x
vi) Cetaceans in CEMP and krill fishery management | High |  |  |  | Dr Kelly, Mr Johannessen
vii) Develop distribution models of harvested and dependent species, and projections using future climate scenarios to inform a risk assessment framework of the likely impacts of climate change (WS-CC-23 Table 1 Recommendation 9, 10, Table 2 Recommendation 20) | Medium |  |  |  | x
viii) Ensure monitoring is adequate to detect significant changes in species life history parameters and identify monitoring data to exchange with adjacent RFMOs e.g. to detect range shifts (WS-CC-23 Table 1 Recommendation 1, 2, 3, 4, 5) | High |  |  | x | x
ix) Identify specific climate variables and metrics useful in communicating the status of AMLR through time (health check). (WS-CC-23 Table 1 Recommendation 24) | High |  |  |  | x
b) Spatial management
i) Science advice on proposals for a Representative System of MPAs | High |  |  |  | Prof Koubbi, Dr Teschke, Dr Krüger | In progress
(1) Current proposals | High |  |  |  | x
(2) Future proposals: Ecoregionalisation of Subantarctic Indian Ocean | Low |  |  |  | Dr Makhado, Dr Koubbi
ii) Research and monitoring plans | High |  |  |  | Dr Devine | In progress
iii) The harmonisation and/or integration of different spatial management initiatives within Subarea 48.1, including the ARK voluntary restricted zones and the D1MPA propoal (SC-CAMLR-41, paragraph 3.65) | High |  |  |  | Dr Santos, Mr Santa Cruz, Dr Lowther, Dr Krüger | In progress
c) By-catch risk assessment for krill and finfish fisheries |  |  |  |  | x
i) Monitoring status and trends | High |  |  |  | Dr E. Kim, Dr Chung | Not yet started |  | x |  | Y
ii) By-catch species catch limits | High |  |  |  | Dr Devine |  |  | x
iii) Review of by-catch decision rules | Medium
iv) Improving by-catch species identification | High | [6 empty] | x
(1) Identification guides | [7 empty] | x
(2) Identification data | [7 empty] | x
v) Biological parameters of by-catch species | High | [6 empty] | SCARFISH
vi) By-catch mitigation methods | Low | [6 empty] | x
d) Incidental mortality
IMAF Task 1: Review of incidental mortality | [6 empty] | x
IMAF Task 1.1 Summary of incidental mortality and interactions at a fine scale (spatial and temporal) | High | [5 empty] | Dr Favero, Mr Walker, Prof Philips |  |  | Y
IMAF Task 1.2 Development of a web-based tool to allow examination of interactions and incidental mortality data across CCAMLR fisheries | Medium | [5 empty] | Dr Favero, Mr Walker, Prof Philips |  |  | Y
i) IMAF Risk Assessment
IMAF Task 3: Seabird and Marine mammals - risk assessment | [6 empty] | x
IMAF Task 3.1 Consider developing risk assessment and/or overlap analysis for seabirds and marine mammals | Medium | [5 empty] | Dr Lindstrøm, Dr Kelly, Prof Philips
IMAF Task 3.2 Use a risk assessment and/or overlap analysis for seabirds and marine mammals | Medium | [8 empty] | Y
ii) Seabird IMAF
IMAF Task 5.1 Power analysis of required observer sampling required for warp strikes | Completed | [5 empty] | Dr Kelly, Dr Hinke, Mr Walker
IMAF Task 5.2 Redesign the warp strike observation protocols | Completed | [5 empty] | Dr Debski |  |  | Y
IMAF Task 5.3 Exploration of approaches to undertake warp strike extrapolations (Note GAM approach recommended by WG-SAM) | High | [5 empty] | Dr Favero, Dr Hinke, Mr Walker |  |  | Y
IMAF Task 5.4 Review required levels of observer sampling for seabird incidental mortality with longline fishery | High | [5 empty] | Mr Zhu, Dr Kawaguchi |  |  | Y
IMAF Task 5.5 Determine composition of stick water resulting from different processing methods from krill trawlers | High | [5 empty] | Dr Favero |  |  | Y
IMAF Task 5.6 Investigate the effect of stick water as an attractor in the immediate vicinity of the vessel | Medium | [5 empty] | Dr Krüger
IMAF Task 5.7 Develop trawl vessel classification based on deployment configurations of fishing gear, processing states and discharge positions to better understand bird strike variability | High | [5 empty] | Dr Krüger |  |  | Y
IMAF Task 6: Seabirds mitigation
IMAF Task 6.1 Consider performance of trawl warp/cable strike mitigiation approaches utilised by continuous trawl vessels (including environmental conditions and other factors) including the improvement and specification development for the 'sock' design | High | [5 empty] | Dr Debski, Dr Arata
IMAF Task 6.2 Review existing use of and consider mitigation requirements in conventional trawl vessels and develop specifications for suitable mitigation | High | [5 empty] | Dr Debski, Dr Arata
IMAF Task 6.3 Review developments in demersal longline mitigation | Completed | [5 empty] | Ms Livesey, Dr Debski, Mr Arangio, Mr McNeill
iii) Marine Mammal IMAF
IMAF Task 2: Marine mammals incidental mortality | [6 empty] | x
IMAF Task 2.1 Refine design of additional data to be collected by observers and crew when whale entangelments occur (see list developed under paragraph 4.17) | Completed | [5 empty] | Dr Kelly (IWC Collaboration), Mr Pardo |  |  | Y
IMAF Task 2.2 Investigate the use of underwater sensors/cameras attached to the net (and A1) to provide information on the occurrence of whale interactions and any subsequent entangelements/capture (continuous) | High | [5 empty] | Dr Kelly (IWC Collaboration), Dr Lowther, Dr Lindstrøm
IMAF Task 2.3 Development of data collection protocols for pinniped mortalities and training materials | Completed | [5 empty] | Mr Pardo |  |  | Y
(1) Implement whale sighting protocols | [9 empty] | Y
IMAF Task 2.4 Review of Elephant seal incidental mortality (including additional information on abundance trends and foraging behaviour for populations affected) | High | [5 empty] | Dr Kelly |  |  | Y
IMAF Task 4: Marine mammals mitigation | [6 empty] | x
IMAF Task 4.1 Review designs of marine mammal exclusion devices and develop specifications for those in use in CCAMLR trawl fisheries (including consideration towards a convex shape to the exclusion mesh to deflect whales (and seals) away from the net mouth) | High | [5 empty] | Dr Kelly (IWC Collaboration), Dr Lowther, Dr Lindstrøm, Dr Ying
IMAF Task 4.2 Undertake experiments into effectiveness of different MMED (for various species) (including performance trails in flume tanks) | Medium | [5 empty] | Dr Kelly (IWC Collaboration), Dr Lowther, Dr Lindstrøm, Dr Ying
e) Habitat protection from fishing impacts |  |  |  |  | x
i) Habitat classification, bioregionalisation and monitoring | Low |  |  |  | x |  |  | x
ii) VME identification and management | Medium |  |  |  | Dr Eléaume, Dr Teschke, Dr Devine et al. | In progress |  | Members |  | Y
iii) Protection of biodiversity and ecosystems (Performance Review 2, Rec 7) | High |  |  |  | x | x |  | Members |  | Y
(1) Ecosystem impacts from krill and finfish fishing, including analyses whether research and sampling design is able to detect such impacts | High for ASAM, Low for FSA |  |  |  | x |  |  | x
(2) Physical disturbance of longline fishing on benthic ecosystems | Low |  |  |  | x |  |  | x
(3) Suitability of reference areas for comparison between fished and unfished areas | Medium |  |  |  | x |  |  | x
f) Monitoring and adaptation to effects of climate change, including acidification |  | x |  |  | x
i) Develop methods to detect change in ecosystems given variability and uncertainty (Performance Review 2, Rec 6) | Medium | x |  |  | Dr Schaafsma, Dr Dahlgren, Dr Hill, Dr Collins, Dr Emmerson, Dr Waluda, Mr Pardo, Dr Cavanagh, Dr Parker, Dr Waluda |  |  | x |  | Y
(1) moored or autonomous platforms |  | Dr Dornan
ii) Develop mechanisms for integration in Scientific Committee Work |  |  |  |  | x | In progress |  |  |  | Y
iii) Develop integrated ecosystem reporting (WG-EMM-2022, paragraph 2.18) | Medium |  |  |  | Mr Pardo, Dr Cavanagh | In progress |  |  |  | Y
(iv) Model to test long-term change in spatial distribution (T18-20 from WS-CC-2023) | Low
Administrative topics
a) Advise on database facilities required through DSAG | High | x |  | x | Dr Devine | In progress | x | DSAG |  | Y
b) Advise on quality control and assurance processes for data provided to and supplied by the Secretariat | High | x |  | x | x |  | x | DSAG |  | Y
c) Refine the scheme of international scientific observation (SISO) across all fisheries | Medium | x |  | x | x |  | x | x |  | Y
1) Finfish | Medium | x |  | x | x |  | x | x |  | Y
2) Krill | High | x |  | x | x |  | x | x |  | Y
d) Further develop data management systems | M | x |  | x | x |  | x | x |  | Y
1) Quality assurance | High | x |  | x | x |  | x | DSAG |  | Y
2) DOI | Medium | [6 empty] | DSAG |  | Y
3) Data access rules | Medium | x |  | x | x |  | x | DSAG |  | Y
e) Communication of progress, internal and external | Medium | x |  | x | x |  | x | x |  | Y
SAM Task 15: Develop a repository of code with examples of standardised diagnostics. | High |  |  | x | [5 empty] | Y
SAM Task 16: Develop a repository for code to estimate biological parameters, including worked examples. | High |  |  | x | [5 empty] | Y
SAM Task 17: Develop code for stock assessment diagnostics and stock status. | High |  |  | x | [5 empty] | Y
f) Working group terms of reference | Low | x |  | x | x |  | x | SC-CAMLR-41 |  | Y
g) Scientific Committee Symposium in 2027 | High | x |  | x | x |  | x | x |  | Y